## Sheet1
Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
February
Present Draft TIP to Internal committees
CDC
CAC
TAC
TCC
EC
March
21 day comment period - send press release
Send comment period press release
Request publication of legal notice
Publish legal notice
Mail stakeholder letters - 21 days
Email stakeholder meeting notication - 13 days
Publish TIP Summary Sheet on webpage
Publish Draft TIP on MPO webpage
Take draft TIP to Lima Public Library
Take draft TIP to Allen County Court House
Take draft TIP to ACRTA
Requests for special TIP formatting
Present Draft TIP to Internal committees
CDC
CAC
TAC
TCC
EC
Placard posting - ltr sent
Community Calendar requests
ODOT publish STIP legal notice
End 21 day comment period
ODOT 14 day comment period
April
Public meeting
Internal committees
CDC
CAC
TAC
TCC
EC
Approve Final TIP
Submit TIP | [26 empty] | ?
|  | task start dates | [10 empty] | internal committees | [8 empty] | last day of month
|  | task complete | [10 empty] | task deadline | [8 empty] | weekends